## Features Tracking
Features Tracking
| Progress | 100%
Feature | Description | Author | Planned start day | Planned end day | Planned amount of time | Planned number of days | Actual start day | Actual end day | Biểu tượng cờ cho Công việc Thực tế Trên/Dưới (theo giờ) | Actual amount of time | Biểu tượng cờ cho Khoảng thời gian Thực tế Trên/Dưới (theo ngày) | Actual number of days | Coding progress | Testing progress | Is delivered | Note
F1 | Login user using JWT | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-12-05 | 2025-02-08 | 1 | 300 | 1 | 63 | 100% | 100% | YES
F2 | Get detail of TODO list by list ID | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-12-29 | 2025-02-01 | 1 | 390 | 0 | 32 | 100% | 100% | YES
F3 | Register user | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-10-31 | 2025-01-12 | 1 | 500 | 1 | 72 | 100% | 100% | YES
F4 | Forgot password | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-11-10 | 2024-11-29 | 1 | 276 | 0 | 19 | 100% | 100% | YES
F5 | Reset passoword with token gets from forgot password feature | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-11-10 | 2024-12-26 | 1 | 310 | 0 | 46 | 100% | 100% | YES
F6 | Refresh access token | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-12-10 | 2024-12-25 | 1 | 510 | 0 | 15 | 100% | 100% | YES
F7 | Create todo task list | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-12-26 | 2025-01-24 | 1 | 790 | 0 | 28 | 100% | 100% | YES
F8 | Remove todo task list | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-12-25 | 2025-02-03 | 1 | 430 | 0 | 38 | 100% | 100% | YES
F9 | Update todo task list | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 200 | 0 | 60 | 100% | 100% | YES
F10 | Get list of TODO lists, including pagination | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 201 | 0 | 60 | 100% | 100% | YES
F11 | Create todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 202 | 0 | 60 | 100% | 100% | YES
F12 | Remove todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 203 | 0 | 60 | 100% | 100% | YES
F13 | Get list of uncompleted TODO tasks, including pagination | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 204 | 0 | 60 | 100% | 100% | YES
F14 | Get list of completed TODO tasks, including pagination | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 205 | 0 | 60 | 100% | 100% | YES
F15 | Get detail of TODO task by task ID | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 206 | 0 | 60 | 100% | 100% | YES
F16 | Modify is in day status of todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 207 | 0 | 60 | 100% | 100% | YES
F17 | Modify is completed status of todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 208 | 0 | 60 | 100% | 100% | YES
F18 | Modify is important status of todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 209 | 0 | 60 | 100% | 100% | YES
F19 | Update content of todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 210 | 0 | 60 | 100% | 100% | YES
F20 | Update note of todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 211 | 0 | 60 | 100% | 100% | YES
F21 | Modify due date of todo task | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2016-03-05 | 2016-05-05 | 1 | 212 | 0 | 60 | 100% | 100% | YES

## External Module Tracking
External Module Tracking
| Progress | 100%
Feature | Description | Author | Planned start day | Planned end day | Planned amount of time | Planned number of days | Actual start day | Actual end day | Biểu tượng cờ cho Công việc Thực tế Trên/Dưới (theo giờ) | Actual amount of time | Biểu tượng cờ cho Khoảng thời gian Thực tế Trên/Dưới (theo ngày) | Actual number of days | Coding progress | Testing progress | Is delivered | Note
FA1 | Integrate with postgressql database using NGPSQL library and also include ASP NET Core Identity database system | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-12-05 | 2025-02-08 | 1 | 300 | 1 | 63 | 100% | 100% | YES
FA2 | Integrate JWT authentication library for JWT auth | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-12-29 | 2025-02-01 | 1 | 390 | 0 | 32 | 100% | 100% | YES
FA3 | Integrate snowflake Id generator library for generating snowflake Id | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-10-31 | 2025-01-12 | 1 | 500 | 1 | 72 | 100% | 100% | YES
FA4 | Intergrate Nswag library for swagger | Jackpieking | 2025-01-10 | 2025-02-10 | 4 | 30 | 2024-11-10 | 2024-11-29 | 1 | 276 | 0 | 19 | 100% | 100% | YES

## Setting
Setting
MEMBER |  | CODING STATUS |  | TESTING STATUS |  | IS DELIVERED
Nickname | Full Name | Status | Description | Status | Description | Status | Description
Jackpieking | Le Khoa | 0 | Not yet | 0 | Not yet | YES | Has delivered
|  | 25% | Just a part | 25% | Just test some part | NO | Has not delivered
|  | 50% | Half of progress | 50% | Half of progress
|  | 75% | So far so good | 75% | More tests have been done
|  | 100% | Done | 100% | Done